## Test Report_Sprint 3
Test Report
Project Name | E-COMMERCE APPLICATION
Stage | Sprint 3
Project Code | CMU-CS246 VIS CasePrint3
Enviroment Setup
Tester
Test Rest | PASS
FAIL
No | Function Name | Sheet Name | Create Date | Test case | Test case pass | Test case fail
1 | Login | Login | 2024-03-21 | 5 | 3 | 2
2 | Register | Register | 2024-03-21 | 4 | 3 | 1
3 | Ucha | Ucha | 2024-03-22 | 6 | 3 | 3
4 | Log in to main word (admin) | Log in to main word (admin) | 2024-03-23 | 3 | 2 | 1
5 | Revenue | Revenue | 2024-03-24 | 13 | 9 | 4
6 | order | order | 2024-03-27 | 10 | 8 | 2
7 | Google map | Google map | 2024-04-02 | 11 | 3 | 8
8 | System | System | 2024-04-10 | 14 | 10 | 4
9 | Customers | Customers | 2024-04-18 | 15 | 11 | 4
10 | Products | Products | 2024-04-20 | 8 | 4 | 4
11 | Log in to main word (personnel) | Log in to main word (personnel) | 2024-04-22 | 5 | 2 | 3
12 | View product information | View product information | 2024-04-22 | 8 | 4 | 4
13 | Create invoices | Create invoices | 2024-05-01 | 3 | 3 | 0
14 | Issue invoices | Issue invoices | 15/5//2024 | 3 | 2 | 1
|  |  |  | 108 | 67 | 41

## Login
Login(Admin end Personnel)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing Date
1 | Login | 1.account: admin 2.password: 1 3.cick login/enter | Logged in successfully | 1 | Hoang Thanh AN | Pass | 2024-03-21

## Register
Register(Admin)
Status | Number Of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing Date
1 | register | 1. Click :Create new account 2. User Name : admin 3. Password : 1 4. re-enter new password: 1 | Sign Up Success | 1 | Hoang Van An | Pass | 2024-03-21

## Ucha
Ucha(Admin)
Status | Number Of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing Date
1 | Enter the Ucha homepage | 1.Click"Ucha"and login | Logged in successfully | 1 | Hoang Thanh An | Pass | 2024-03-22

## Revenue
Revenue(Admin)
Status | Number Of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing Date
1 | Revenue | 1: login successfully 2: click on Revenue | Show Revenue | 1 | Hoang Van AN | Pass | 2024-03-24

## Order
Order(Admin)
Status | Number Of Tasks
Pass | 1
Fail | 1
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing date
1 | Order | 1: login successfully 2: click on order | Show Order | 1 | Hoang Thanh An | Pass | 2024-03-27

## Google map
Google map(Admin end Personnel)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing date
1 | Google map | 1: login successfully 2. Click Google map | Show Google map | 1 | Hoang Thanh An | Pass | 2024-04-02

## System
System(Admin)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing date
1 | System | 1: login successfully 2. Click System | Show System | 5 | Hoang Van Duong,Hoang Thanh An,Dao Tien Dung,Nguyen Viet Minh Man.Tran Quoc Quang | Pass | 2024-05-12

## Customers
Customers(Admin)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing date
1 | Customers | 1: login successfully 2. Click Customers | Show Customers | 2 | Hoang Van Duong,Hoang Thanh An | Pass | 2024-04-18

## Products
Products(Admin)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test Steps | Desired results | Priority | Role | Status | Testing date
1 | Products | 1: login successfully 2. Click Products | Show Products | 2 | Tran Qoc Quang | Pass | 2024-04-20

## View product information
View product information(Personnel)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Statuss | Testing date
1 | View product information | 1: login successfully 2. Click View product information | Show View product information | 1 | Hoang Van An | Pass | 2024-05-10

## Create invoices
Create invoices(Personnel)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Statuss | Testing date
1 | Create invoices | 1: login successfully 2. Click Create invoices | Show Create invoices | 1 | Hoang Van An | Pass | 2024-05-10

## Issue invoices
Issue invoices(Personnel)
Status | Number of Tasks
Pass | 1
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Statuss | Testing date
1 | Issue invoices | 1: login successfully 2. Click Issue invoices | Show Issue invoices | 1 | Hoang Van An | Pass | 2024-05-10