## Product Backlog
[11 empty] | Level | Priority |  |  |  | Estimate
[11 empty] | 1 | High |  |  |  | Estimated time to complete the work (hour)
[11 empty] | 2 | Medium
[11 empty] | 3 | Low
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Login | Admin, Staff | access to the Application by my account | The application fits my role, thus I can utilize it. | Once the user enters their password and email address correctly, they can log in and access the system. - When processing, produce error or success signals. - When the value is invalid, display the error messages. |  | 1 |  |  |  | 1~2 | 20
PB02 | Logout | Admin, Staff | logout of the system | I can stop using the system. | User log out of the system when User click the icon logout |  | 2 |  |  |  | 1~2 | 32
PB03 | Register | Admin | create my account | I can use that account to login the system. | By inputting their email address, password, and username, users may establish new accounts. - There must be email. - Enter email addresses correctly. - Special characters and spaces are not used in emails. The password is space-free. - When processing, produce an error or success message. When a value is deemed invalid, an error message is presented. |  | 1 |  |  |  | 1 | 36
PB04 | Change Password | Admin, Staff | change my password | i can make my account better secured | - User clicks [Change password] button, the system will go to the change password page - User will enter the old password, new password and re-enter the new password + Then click [Save] button + If the user enters the correct old password, it is allowed to change the password - If the old password is wrong, display the message [Old password is incorrect] and do not change the password |  | 2 |  |  |  | 1~2 | 18
PB05 | Use Caculator | Admin, Staff | There is a tool to calculate money | t can open the calculator at the home page | I can select the [settings] icon and then select [calcular] to calculate as needed |  | 2 |  |  |  | 1~2
PB06 | Show Dashboard | Admin | show a dashboard | I can improve the system's productivity. | - Admin clicks [Show Dashboard]. Show detailed information. |  | 1 |  |  |  | 2 | 15
PB07 | Change Account Information | Admin, Staff | Change my personal Infomation | I can change the personal ìnormation in the application | User and Final Party Users have access to a "Profile" area where they can edit all personal information. |  | 2 |  |  |  | 1~2 | 10
PB8 | Manage accounts Staff | Admin | Add or remove account personnel | I can Add or remove account personnel | When the administrator clicks [ADD], the system will navigate to a website where the administrator can check Staff details. If the administrator presses [Cancel], the function will end. |  | 1 |  |  |  | 1 | 10
P9 | See Staff List | Admin | found Staff list | I can see my Staff list | When I want to see the list of employees, I select [Staff], the employee list will appear with the employee's name, phone number, address, and account information. |  | 1 |  |  |  | 1 | 12
PB10 | Add Product | Admin | more goods | I can add products | Find and select the function or button to add a new order. Typically this will be an icon or button labeled "More".Enter order information Confirm and save order: Review the information entered and make sure it is correct and complete. Then select "Confirm" to add the order to the system. Check for updates: Once an order is added, you can check the order list again and make any updates as needed, such as changing the order status or adding note. |  | 1 |  |  |  | 1 | 24
PB11 | View product information | Admin | See product information | I can see product information | After entering, you can click on the product to view product information |  | 1 |  |  |  | 1 | 8
PB12 | See Highest Rated | Admin | See product reviews | I can see product reviews | In the product list there will be the highest rated products |  | 1 |  |  |  | 1 | 6
PB13 | Create Order | Admin | Create orders for admin to use | t can create orders for admin to use | Go to the order section, click [product] and then enter order information |  | 1 |  |  |  | 1 | 14
PB14 | Total, Error, Successful Order | Admin | View order status | I can see whether the order was successful or failed | In order information, there will be parameters about total revenue, number of defective orders, and number of successful orders |  | 1 |  |  |  | 1 | 26
PB18 | See Order List | Admin | See order list | I can see the list of orders | After logging in with the admin account, view the order list by selecting the goods icon |  | 1 |  |  |  | 1 | 8
PB15 | Delete Order | Admin | Delete error orders | I can delete orders that are in error | Select the order to delete and select [delete] |  | 1 |  |  |  | 1 | 8
PB16 | See Client Information | Admin | View customer information | I can view customer purchase information | To view customer information, click on the label[person] to view customer information including their name, email, phone number, and order. |  | 1 |  |  |  | 1 | 8
PB17 | Revenue Management | Admin | money management | I can manage the revenue from the store | Revenue Management |  | 1 |  |  |  | 1 | 8
PB18 | See Product List | Admin, Staff | products are visible | You can see the products in the product list section | When I want to see my product list I can Click on the [row] icon |  | 2 |  |  |  | 1~2 | 32
PB19 | Create Invoice | Staff | Create orders for customers | I can create an invoice and it can calculate the total amount due | Register with a staff account, then select the products the customer chooses to buy and click [in] to print the invoice |  | 2 |  |  |  | 1~2 | 6
PB20 | See Invoice List | Staff | See list of invoices | I can see a list of invoices and know which invoices have been paid and which have not been paid | After entering with the employee account, select view invoice list to view the invoice list |  | 2 |  |  |  | 1~2 | 8
Note on M7: ====== ID#AAAAev_bIv4 jan samuelsson (2022-08-26 07:29:29) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Main (hidden)
Project | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint # | Start | End | Status | Work / Estimates Committed | Work spent Delivered | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2023-03-15 | 2023-04-12 | Complete | 21 | 21
[6 empty] | 2 | 2023-04-13 | 2023-05-01 | Complete | 21 | 20
[6 empty] | 3 | 2023-05-02 | 2023-05-22 | Complete | 21 | 23
Formulas:
Project #1 = [Start]+28
Start = [Project #1, row above]+1

## Sprint 1 Backlog
Sprint Backlog
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18
1.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 |  | Create Sprint backlog for Sprint 1 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 |  | Create Test Plan document for Sprint 1 | All members | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 |  | Create Database document for Sprint 1 | All members | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 2 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 |  | Design GUI for the admin to Login | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | Design GUI for the admin to Logout | An, Quang | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | Design GUI for the admin to Register | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 |  | Design GUI for the admin to Change Password | An, Quang | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 |  | Design GUI for the admin to Use Caculator | An, Duong | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 |  | Design GUI for the admin to Show Dashboard | An | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.11 |  | Design GUI for the admin to Change Account Information | Dung | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.12 |  | Design GUI for the admin to Store Branch Management | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.13 |  | Design GUI for the admin to Manage accounts Staff | An, Man | Done | 2 | 2 | 0 | 2 | On Schedule | Day 6: 2; Day 7: 0
1.14 |  | Design GUI for the admin to See Staff List | An, Man | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.15 |  | Design GUI for the admin to Add Product | Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.16 |  | Design GUI for the admin to View product information | An, Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.17 |  | Design GUI for the admin to See Highest Rated | Quang | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.18 |  | Design GUI for the admin to Create Order | An | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.19 |  | Design GUI for the admin to Total, Error, Successful Order | An, Dung | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 |  | Design GUI for the admin to See Order List | An, Dung, Man | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.21 |  | Design GUI for the admin to Delete Order | An, Dung | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.22 |  | Design GUI for the admin to See Client Information | An, Duong | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.23 |  | Design GUI for the admin to Revenue Management | An, Dung | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.24 |  | Design GUI for the admin to See Product List | An, Man | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.25 |  | Design GUI for the admin to Create Invoice | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.26 |  | Design GUI for the admin to See Invoice List | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.27 |  | Design Test case | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.28 |  | Code Frontend for the admin to Login | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.29 |  | Code Frontend for the admin to Logout | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 |  | Code Frontend for the admin to Register | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.31 |  | Code Frontend for the admin to Change Password | An, Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.32 |  | Code Frontend for the admin to Use Caculator | An, Duong | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.33 |  | Code Frontend for the admin to Show Dashboard | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.34 |  | Code Frontend for the admin to Change Account Information | Duong | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.35 |  | Code Frontend for the admin to Store Branch Management | An, Man | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1.36 |  | Code Frontend for the admin to Manage accounts Staff | Dung | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1.37 |  | Code Frontend for the admin to See Staff List | Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1.38 |  | Code Frontend for the admin to Add Product | An, Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
1.39 |  | Code Frontend for the admin to View product information | Quang | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1.4 |  | Code Frontend for the admin to See Highest Rated | An,Quang | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1.41 |  | Code Frontend for the admin to Create Order | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
1.42 |  | Code Frontend for the admin to Total, Error, Successful Order | An, Dung | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
1.43 |  | Code Frontend for the admin to See Order List | Dung, Man | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0
1.44 |  | Code Frontend for the admin to Delete Order | An, Dung | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
1.45 |  | Code Frontend for the admin to See Client Information | An, Duong | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
1.46 |  | Code Frontend for the admin to Revenue Management | An, Dung | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
1.47 |  | Code Frontend for the admin to See Product List | An, Man | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
1.48 |  | Code Frontend for the admin to Create Invoice | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
1.49 |  | Code Frontend for the admin to See Invoice List | Quang | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
1.5 |  | Code Backend for the admin to Login | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
1.51 |  | Code Backend for the admin to Logout | Dung | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
1.52 |  | Code Backend for the admin to Register | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1.53 |  | Code Backend for the admin to Change Password | An, Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1.54 |  | Code Backend for the admin to Use Caculator | Duong | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1.55 |  | Code Backend for the admin to Show Dashboard | Dung | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
1.56 |  | Code Backend for the admin to Change Account Information | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
1.57 |  | Code Backend for the admin to Store Branch Management | Quang | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
1.58 |  | Code Backend for the admin to Manage accounts Staff | Duong | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
1.59 |  | Code Backend for the admin to See Staff List | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
1.6 |  | Code Backend for the admin to Add Product | An, Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
1.61 |  | Code Backend for the admin to View product information | Quang | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0
1.62 |  | Code Backend for the admin to See Highest Rated | Quang | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
1.63 |  | Code Backend for the admin to Create Order | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
1.64 |  | Code Backend for the admin to Total, Error, Successful Order | An, Dung | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
1.65 |  | Code Backend for the admin to See Order List | Dung, Man | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1.66 |  | Code Backend for the admin to Delete Order | Dung | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1.67 |  | Code Backend for the admin to See Client Information | An, Duong | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
1.68 |  | Code Backend for the admin to Revenue Management | Dung | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
1.69 |  | Code Backend for the admin to See Product List | An, Man | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
1.7 |  | Code Backend for the admin to Create Invoice | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
1.71 |  | Code Backend for the admin to See Invoice List | Dung | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
1.72 |  | Testing | All members | Done | 5 | 5 | 0 | 5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
1.73 |  | Fix bug | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
1.74 |  | Re-Testing | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
1.75 |  | Sprint 1 Review Meeting | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
1.76 |  | Release Sprint 1 | All members | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | Total | 160 | 160 | 0 | 143 |  | 8 | 6 | 6 | 1 | 4 | 6 | 9 | 10 | 11 | 11 | 11 | 11 | 12 | 14 | 15 | 6 | 9 | 10
|  |  |  | Burn down | [5 empty] | 152 | 146 | 140 | 139 | 135 | 129 | 120 | 110 | 99 | 88 | 77 | 66 | 54 | 40 | 25 | 19 | 10 | 0
|  |  |  | Burn up | [5 empty] | 8 | 14 | 20 | 21 | 25 | 31 | 40 | 50 | 61 | 72 | 83 | 94 | 106 | 120 | 135 | 141 | 150 | 160
[5 empty] | Member | Estimate
[5 empty] | Man,Nguyen Viet Minh | 10.25
[5 empty] | An,Hoang Thanh | 50.25
[5 empty] | Dung,Dao Tien | 18.75
[5 empty] | Duong,Hoang Van | 18.25
[5 empty] | Quang,Tran Quoc | 26.25
[5 empty] | Total | 123.75

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Sprint Backlog | [19 empty] | 5/2/2024-5/25/2024
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
1.77 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.78 |  | Create Sprint backlog for Sprint 2 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.79 |  | Create Test Plan document for Sprint 2 | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 |  | Create Database document for Sprint 2 | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.81 | PB01 | Design UI for the staff to Login | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.82 |  | Design UI for staff to Logout | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.83 | PB05 | Design UI for staff to Change password | An, Quang | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.84 |  | Design UI for staff to Use Caculator | An, Duong | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.85 |  | Design UI for staff to Change Account Information | An | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.86 | PB11 | Design UI for staff to See Product List | An, Man | Done | 1 | 1 | 0 | 1 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.87 | PB06 | Design UI for staff to Create Invoice | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.88 | PB02 | Design UI for staff to See Invoice List | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.89 |  | Design Test case | All members | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9 | PB01 | Code Frontend for the staff to Login | An | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.91 | PB02 | Code Frontend for staff to Logout | An | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.92 | PB05 | Code Frontend for staff to Change password | An, Quang | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.93 | PB11 | Code Frontend for staff to Use Caculator | An, Duong | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.94 | PB06 | Code Frontend for staff to Change Account Information | An | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.95 | PB21 | Code Frontend for staff to See Product List | An, Man | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.96 | PB02 | Code Frontend for staff to Create Invoice | An | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
1.97 | PB01 | Code Frontend for staff to See Invoice List | Dung | Done | 5 | 5 | 0 | 5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0
1.98 | PB02 | Code Backend for the staff to Login | An | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
1.99 | PB05 | Code Backend for staff to Logout | An | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
2 | PB11 | Code Backend for staff to Change password | An, Quang | Done | 5 | 5 | 0 | 5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0
2.01 | PB18 | Code Backend for staff to Use Caculator | An, Duong | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
2.02 | PB06 | Code Backend for staff to Change Account Information | An | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
2.03 | PB21 | Code Backend for staff to See Product List | An, Man | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
2.04 |  | Code Backend for staff to Create Invoice | An | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
2.05 | PB02 | Code Backend for staff to See Invoice List | An | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
2.06 |  | Testing | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
2.07 | 2.27 | Fix bug | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
2.08 |  | Re-Testing | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2.09 | 2.27 | Sprint 2 Review Meeting | All members | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
2.1 | 2.27 | Release Sprint 2 | All members | Done | 2 | 2 | 0 | 2 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | Total | 112 | 112 | 0 | 112 |  | 8 | 4 | 8 | 4 | 2 | 3 | 1 | 2 | 5 | 10 | 3 | 4 | 7 | 5 | 7 | 6 | 7 | 9 | 10 | 7
|  |  |  | Burn down | [5 empty] | 104 | 100 | 92 | 88 | 86 | 83 | 82 | 80 | 75 | 65 | 62 | 58 | 51 | 46 | 39 | 33 | 26 | 17 | 7 | 0
|  |  |  | Burn up | [5 empty] | 8 | 12 | 20 | 24 | 26 | 29 | 30 | 32 | 37 | 47 | 50 | 54 | 61 | 66 | 73 | 79 | 86 | 95 | 105 | 112
[5 empty] | Member | Estimate
[5 empty] | Man,Nguyen Viet Minh | 10.75
[5 empty] | An, Hoang Thanh | 52.25
[5 empty] | Quang, Tran Quoc | 15.75
[5 empty] | Dung,Dao Tien | 15.25
[5 empty] | Duong,Hoang Van | 15.25
[5 empty] | Total | 98.5

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart