## Test report _ sprint 1
Test Report
Project Name | Team 4
Stage | Sprint 1
Project Code | CMU-CS246 VIS CasePrint1
Enviroment Setup
Tester | Hoang Thanh An
Test Rest | PASS
FAIL
No | Function Name | Sheet Name | Create Date | Test case | Test case pass | Test case fail
1 | Login | Login | 2024-03-21 | 5 | 3 | 2
2 | Register | Register | 2024-03-21 | 4 | 3 | 1
3 | Captcha | Captcha | 2024-03-22 | 6 | 3 | 3
4 | Log in to main word (admin) | Log in to main word (admin) | 2024-03-23 | 3 | 2 | 1
5 | Revenue | Revenue | 2024-03-24 | 13 | 9 | 4
6 | Order | Order | 2024-03-27 | 10 | 8 | 2
7 | Google map | Google map | 2024-04-02 | 11 | 3 | 8
8 | System | System | 2024-04-10 | 14 | 10 | 4
9 | Customers | Customers | 2024-04-18 | 15 | 11 | 4
10 | Products | Products | 2024-04-20 | 8 | 4 | 4
11 | Log in to main word (personnel) | Log in to main word (personnel) | 2024-04-22 | 5 | 2 | 3
12 | View product information | View product information | 2024-04-22 | 8 | 4 | 4
13 | Create invoices | Create invoices | 2024-05-01 | 3 | 3 | 0
14 | Issue invoices | Issue invoices | 15/5//2024 | 3 | 2 | 1
|  |  | Total | 108 | 67 | 41

## Login(ADMIN)
Login(ADMIN)
Status | Number of Tasks
Pass | 5
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing Date
1 | Login | 1. Account: admin 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ thường" | 1 | Hoang Thanh An | Pass | 2024-03-21
2 | Login | 1. Account: admin 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ hoa " | 1 | Tran Quoc Quang | Pass | 2024-03-22
3 | Login | 1. Account: admin 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ thường" | 1 | Dao Tien Dung | Pass | 2024-03-22
4 | Login | 1. Account: admin 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự đặc biệt" | 1 | Nguyen Viet Minh Man | Pass | 2024-03-22
5 | Login | 1. Account: admin 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ thường" | 1 | Hoang Van Duong | Pass | 2024-03-23

## Login(personnel)
Login(personnel)
Status | Number of tasks
Pass | 5
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing Date
1 | Register | 1. Enter account name:nhanvien 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ thường" | 1 | Hoang Thanh An | Pass | 2024-03-21
2 |  | 1. Enter account name:nhanvien 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ hoa " | 1 | Tran Quoc Quang | Pass | 2024-03-22
3 |  | 1. Enter account name:nhanvien 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ thường" | 1 | Dao Tien Dung | Pass | 2024-03-22
4 |  | 1. Enter account name:nhanvien 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự đặc biệt" | 1 | Nguyen Viet Minh Man | Pass | 2024-03-22
5 |  | 1. Enter account name:nhanvien 2. Password: 1 3. Click login/Enter | Loggin failed system return " phải có ít nhất một kí tự chữ thường" | 1 | Hoang Van Duong | Pass | 2024-03-23

## Enter the main homepage user
Enter the main homepage
Status | Number Of Tasks
Pass | 2
Fail | 0
No | Test case name | Test steps | Desired results | Priority | Role | Status | Testing Date
1 | Enter the main homepage | 1. Enter "home page" | Products | 1 | Tran Quoc Qang | Pass | 2024-04-20
2 | Enter the main homepage | 1. Enter "home page" | Revenue | 1 | Hoang Thanh An | Pass | 2024-03-24

## EditRevenue
Buy Medicine
Status | Number Of Tasks
Pass | 2
Fail | 0
No | Buy Phone | Test steps | Desired results | Priority | Role | Status | Testing Date
1 |  | 1.click "Revenue" | Information changed successfully | 2 | Hoang Thanh An | Pass | 3/20/2024
2 |  | 1.click "Revenue" | Information changed successfully | 2 | Hoang Thanh An | Pass | 2024-03-21

## View Cart
View map
Status | Number Of Tasks
Pass | 3
Fail | 0
No | View Revenue chart | Test steps | Desired results | Priority | Role | Status | Testing Date
1 |  | 1. Click Revenue chart | Successful rise and fall and price change | 1 | Hoang Thanh An | Pass | 2024-04-16
2 |  | 1. Click Revenue chart | Successful rise and fall and price change | 1 | Hoang Thanh An | Pass | 2024-04-17
3 |  | 1. ClickRevenue chart | Successful rise and fall and price change | 1 | Hoang Thanh An | Pass | 2024-04-18

## Product
View map
Status | Number Of Tasks
Pass | 3
Fail | 0
No | Product | Test steps | Desired results | Priority | Role | Status | Testing Date
1 |  | 1. Search for products 2. Show product information 3. Edit product information 4. Delete product 5. add products | Successful product search | 1 | Hoang Thanh An, Tran Quoc Quang | Pass | 2024-04-20
2 |  | 1. Search for products 2. Show product information 3. Edit product information 4. Delete product 5. add products | Search for products, Demonstrate successful product intelligence | 1 | Hoang Thanh An, Tran Quoc Quang | Pass | 2024-04-21
3 |  | 1. Search for products 2. Show product information 3. Edit product information 4. Delete product 5. add products | Search for products, Show product information, edit product information, delete products , added product successfully | 1 | Hoang Thanh An, Tran Quoc Quang | Pass | 2024-04-21

## List of orders
View map
Status | Number Of Tasks
Pass | 3
Fail | 0
No | List of orders | Test steps | Desired results | Priority | Role | Status | Testing Date
1 |  | 1.Login : nhan vien 2. Password : "1" 3. List of orders | Display the list and select orders | 1 | Hoang Thanh An | Pass | 3/21/2024
2 |  | 1.Login : nhan vien 2. Password : "1" 3. List of orders | Display the list and select orders | 1 | Dao Tien Dung | Pass | 3/21/2025
3 |  | 1.Login : nhan vien 2. Password : "1" 3. List of orders | Display the list and select orders | 1 | Nguyen Viet Minh Man | Pass | 3/21/2026

## See Guest Information
View map
Status | Number Of Tasks
Pass | 2
Fail | 0
No | See Guest Information | Test steps | Desired results | Priority | Role | Status | Testing Date
1 |  | 1.Login : admin 2. Password : "1" 3. List of orders | Show Guest Information | 1 | Hoang Thanh An | Pass | 3/21/2024
2 |  | 1.Login : admin 2. Password : "1" 3. List of orders | Show Guest Information | 1 | Hoang Van Dương | Pass | 3/21/2024